## Sheet1
Activity | Data Source | Owner | Checkpoint #1 | Checkpoint #2 | Est. Completion
Setup the project |  | Lexi | 2024-04-10 | 2024-04-14
Git repository | N/A |  | Setup code & send to team | 2nd draft code - feedback
csv & api Files | N/A
Branch / Merge | N/A
Understanding customer demand to inform investment decisions |  | Brittany | 2024-04-13 | 2024-04-14
Analyze most popular Top 10 cities in U.S. | Column 17 in csv |  | 1st draft code | 2nd draft code - feedback
Analyze least popular Bottom 10 cities in U.S. | Column 17 in csv
Analyze most expensive Top 10 cities in U.S. | Columns 10 & 17 in csv
Analyze least expensive Bottom 10 cities in U.S. | Columns 10 & 17 in csv
Understanding customer behavior to inform types and styles |  | Vlad | 2024-04-13 | 2024-04-14
Find Mean, Median, Mode for number of days available for AirBnB | Column 16 in csv |  | 1st draft code | 2nd draft code - feedback
Determine if Mean or Median better (depending on dataset) | Column 16 in csv
Analyze most popular timeframes for Top 10 cities in U.S. | May not have data available
Analyze least popular timeframes for Top 10 cities in U.S. | May not have data available
Analyze rain impact on average number of days available (from weather API) | May not have data available
Understanding historical data and correlations to project future plans |  | Lexi | 2024-04-13 | 2024-04-14
Compare 2020 to 2023 number of rentals | 2 csvs |  | 1st draft code | 2nd draft code - feedback
Compare 2020 to 2023 price of rentals | 2 csvs
Compare 2020 to 2023 reviews of rentals | 2 csvs
Determine if COVID (2020) had an impact on data compared to non-COVID (2023)
Review & quality testing of the project |  | Abigail | N/A | 2024-04-14
Validate each section makes sense | N/A |  |  | 1st draft analysis
Create cohesive analysis from data | N/A
Summarize outcomes & build presentatoin | N/A